## Risk Register - Home
UW174(RM) 09/21 (ORR) | Last review:
Contents
[Insert Organisation name]
Strategic Objectives
Risk Register
Assessment Criteria
Risk
Register
Guidance
@
Risk Map
.
.
.
.
.
.

## Strategic Objectives
(Insert organisation name & strategic objectives (examples)): 1. To increase awareness of the organisation through improved marketing activity to deliver required numbers
- Metrics: Financial targets associated with sales
2. To maintain compliance with key legislation and regulatory requirements
- Metrics : Early warning indicators around compliance / complaints 3. To encourage a culture of pride and trust across the organisation - Metrics: retention of all employees
4. To operate as an efficient, safe and sustainable organisation
- Metrics: carbon and energy reduction targets, incident reporting
*Strategic Objectives and Metrics listed above are illustrative rather than definitive. You are encouraged to refine the statements above and to develop Key Performance Indicators (KPIs) against which to monitor your strategic objectives.
Back to Contents

## Risk Register - template
[Insert organisation name] - Risk Register |  |  |  | KEY
|  |  |  | Risk Category | Risk Map ID Letter | Risk Score Impact | Likelihood |  | Risk Score
Updated / Reviewed - [Insert Date] |  |  |  | Strategic Operational People Legal / Regulatory Financial Hazard | A B C D E F | 1 - Insignificant 2 - Minor 3 - Moderate 4 - Major 5 - Extreme/catastrophic |  | 1 - Remote 2 - Unlikely 3 - Possible 4 - Probable 5 - Highly probable | 1-5 - Low 6-10 - Medium 11-25 - High
Risk Information |  |  |  |  | Inherent Risk Score | [6 empty] | Residual Risk Score
Risk No | Risk Map ID | Risk Description | Risk Causes | Consequences | Impact | Likelihood | Risk Score | Current Risk Mitigation Measures | Risk Owner | Strategic Objectives | Risk Category | Impact | Likelihood | Risk Score | Ongoing or planned mitigation measures | Target Completion Date
Refer to Key above
Risk No | Record the Risk category & sequential No | Identify the risk headline detail | Identify the route cause/s | Identify the potential consequences | 1 - 5 | 1 - 5 | Total | Identify what current controls are in place | Who is responsible? | Link the risk to your strategic objective/s | Link to a risk category and refer to key | 1 - 5 | 1 - 5 | Total | Identify what additional controls or actions you need to put in place | Identify a target date for completion
1 | C1 | Managing mental health & well being of employees | Increased/excessive workload, lack of support, health problems | Employee burnout, sickness, impact on delivery of services | 5 | 3 | 15 | Mental health support | Head of Human Resources | 1 | People | 5 | 3 | 15 | Introduce a counselling service, complete mindfulness training and regular one-to-one support | 31.12.2020
2 | C2 | Recruitment & retention of employees | Poor reputation, changes to pension scheme, workload | Inability to recruit and retain employees, impact on delivery of objectives | 4 | 4 | 16 | Promotion, attractive package, flexible working conditions, good line management support | Head of Human Resources | 1 | People | 3 | 3 | 9 | Enhance the existing training & development programme. Increased promotion of the organisation | 31.12.2020
3 | D1 | Political environment creating uncertainty in the sector | Change in Government leading to changes in policies | Changes in working hours | 4 | 2 | 8 | Horizon scanning | Head of Operations | 2 | Legal / Regulatory | 4 | 2 | 8 | Ongoing environmental scanning | 31.04.2021
4 | B1 | Costs of maintaining buildings | Incident to building (Fire, Flood), severe weather | Additional repair and maintenance costs. | 4 | 4 | 16 | Routine building maintenance plans. Business Continuity Plans. On site Site Manager. | Site Manager | 2 | Operational | 3 | 3 | 9 | Review of Business Continuity Plans. Planned and regular maintenance and inspection of building for wear and tear. | 31.12.2020
5 | D2 | Impact of Brexit | Brexit | Reduction in income. Some employee’s no longer able to work here. | 3 | 4 | 12 | Horizon scanning | Head of Operations | 2 | Legal / Regulatory | 3 | 4 | 12 | Ongoing environmental scanning. Succession planning. Increase marketing activity. | 31.12.2020
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
Back to Contents

## Guidance
Risk Register Guidance
| Description | Guidance
Risk ID | A simple, sequential reference number for identifying the risk in the register and on the heat map. The letter indicates the risk category | Number should be the next number after the risks on the risk register (accounting for any removed / closed out risks), and the letter should correspond with the risk category. Example: B1
Risk Description | A brief outline of the risk scenario | This should be a specific and realistic scenario, articulating the risk in a concise way. Example: Loss of key member of staff responsible for Health & Safety
Risk Causes | Events or situations that can cause the risk to materialise or the controls to fail | A list of processes, actions or events that may allow the risk to crystallise or the controls to fail. Example: Long term sick leave
Risk Consequences | If the risk occurred, what would the potential outcomes be? | Give credible outcomes that may impact the charity if the risk crystallised. Example: Lack of expertise in Health & Safety, failure to create safe working environment
Inherent Risk Score | Inherent impact, likelihood and risk score before controls | Use the Risk Assessment Criteria guidance to score risks before controls are implemented.
Current Risk Mitigation Measures | List of the current controls in place | List of current measures to limit or prevent the risk from materialising. Example: Cross-skilling of current staff
Risk Owner | The individual / team accountable for the risk with enough authority to implement action | The person / team is accountable and can authorise action. The owner should be the 'go to' person if you needed further information on the risk. Example: Name / Title
Strategic Objectives | The strategic objective linking to the risk | Link the risk to your most relevent strategic objective.
Risk Category | Describes the risk category relating to the risk | Risk categories are outlined in more detail below. Example: Operational
Residual Risk Score | Residual impact, likelihood and risk score after controls | Use the Risk Assessment Criteria guidance to score risks after controls have been implemented.
Ongoing or planned mitigation measures | Provides detail behind the actions planned to limit / mitigate the risk going forward | List of actions that will be undertaken to limit / mitigate the risk further. Example: Quarterly review of staff competencies
Target Completion Date | Intended date for when planned mitigation measures will be in place | Indication around the time it will take to implement the necessary mitigation measures. Example: 31.07.17
Risk Category Options | Description | Guidance
| Strategic | Strategic risks are uncertain future events that could negatively impact the achievement of your charity’s vision and strategic objectives
| Operational | Operational risks are uncertain future events that could negatively impact the day to day operations of the organisation
| People | People risks are uncertain future events that could negatively impact on staff, volunteers of the organisation, or the people it interacts with
| Legal / Regulatory | Regulatory risks are uncertain future events that could negatively impact the organisation's ability to comply with the legal / regulatory landscape
| Financial | Financial risks are uncertain future events that could negatively impact the financials of the organisation
| Hazard | Hazard risks are uncertain future events that negatively impact on the organisation, caused by a hazard of some sort
Back to Contents

## Risk Assessment Criteria
Risk Assessment Criteria
Risk Likelihood Measurement Criteria
Scale | Description | Likelihood of Occurrence | Probability of Occurrence
1 | Remote | 1 - 5% - (1 in 20 yrs) | May only occur in exceptional circumstances
2 | Unlikely | 6 - 15% - (1 in 6/7 yrs) | Expected to occur in a few circumstances
3 | Possible | 16 - 40% - (1 in 2/3 yrs) | Expected to occur in some circumstances
4 | Probable | 41 - 75% - (1 in 2 yrs) | Expected to occur in many circumstances
5 | Highly probable | 76 - 100% - (1 in less than 2 yrs) | Expected to occur frequently and in most circumstances
Risk Impact Measurement Critieria
Scale | Description | Service / Operations | Safety / People | Financial
1 | Insignificant | ■ No impact on service ■ No impact on reputation ■ Compliant unlikely ■ Litigation risk remote | ■ No fatalities ■ Minor impact on people's health | 1 - 2 % of turnover
2 | Minor | ■ Slight impact on service ■ Slight impact on reputation ■ Complaint possible ■ Litigation possible | ■ No fatalities ■ A small number of minor injuries (3 - 4) requiring first aid treatment | 3 - 5 % of turnover
3 | Moderate | ■ Some service disruption ■ Potential for adverse publicity - avoidable with careful handling ■ Complaint probable ■ Litigation probable | ■ No fatalities ■ Significant number of people affected requiring first aid treatment | 5 - 8% of turnover
4 | Major | ■ Service disrupted ■ Adverse publicity not avoidable (local media) ■ Complaint probable ■ Litigation probable | ■ Significant number of people affected ■ Hospitalisation required as well as medical treatment | 8 - 15% of turnover
5 | Extreme / Catastrophic | ■ Service interrupted for a significant time ■ Major adverse publicity not avoidable (national media) ■ Major litigation expected ■ Resignation of senior management and board ■ Loss of beneficiary confidence | ■ Fatality / fatalities ■ Large number of people affected ■ Multiple serious or extensive injuries | 15% + of turnover
Back to Contents

## Data (hidden)
Risk Register | Action Plan
Risk Category | Review Period | Current Controls | Improvement Potential | Priority
Strategic | Daily | Poor | Difficult | High
Operational | Weekly | Average | Moderate | Medium
People | Monthly | Good | Easy | Low
Legal / Regulatory | Bi-monthly
Financial | Quarterly
Hazard | 6 Monthly
Annually
Risk Map Axis
X Axis |  |  | Y Axis
X | Y | Label | X | Y | Label
1 | 0.5 | Remote | 0.5 | 1 | Insignificant
2 | 0.5 | Unlikely | 0.5 | 2 | Minor
3 | 0.5 | Possible | 0.5 | 3 | Moderate
4 | 0.5 | Highly probable | 0.5 | 4 | Extreme / Catastrophic
Risk Trend |  | Types of Control |  | Insurance Programme Response | Insurability Potential
Stable |  | Preventative |  | Insured | Insurable
Accelerating |  | Corrective |  | Partially Insured | Partially Insurable
Fading |  | Directive |  | Not Insured | Not Insurable
Detective